## Dashboard
EXECUTIVE BUSINESS DASHBOARD
Today's Top 3 | [5 empty] | Workflow Bottlenecks
No. | Project | Activity | Health | Due |  | No. | Project | Activity | Health | Due
1 | FY26 Budget | Finalize Q2 budget before board meeting | Yellow | 2025-04-29 |  | 1 | NDA | Legal hasn’t reviewed a contract in 10 days | Red | 2025-04-29
2 | New Billing System | Activity 6 | Yellow | 2025-04-29 |  | 2
3 | [5 empty] | 3
Project Tracker
No. | Project | Activity | Health | Due |  | Owner |  | Notes
1 | New CRM | CRM migration (Q2 goal) | Red | 2025-04-29 |  | Emp 2 |  | 4/1: Testing in Sandbox
2 | New Contract Temp | Revise current template | Red | 2025-04-29 |  | Emp 4 |  | 0
3 | New Hardware | Activity 2 | Yellow | 2025-04-29 |  | Emp 5 |  | 0
Transactional Tasks | [5 empty] | Automation Center
No. | Project | Activity | Health | Due |  | No. | Project | Activity | Health | Due
1 | No Data Found For Today | #VALUE! | #VALUE! | #VALUE! |  | 1 | Project F | Activity 15 | Yellow | 2025-04-29
2 | [5 empty] | 2 | Project H | Activity 17 | Yellow | 2025-04-29
3 | [5 empty] | 3
Parking Lot
No. | Project | Category | Health | Department | Activity | Status | Owner | Start Date | Due Date | Notes
1 | Billing | Transactional Tasks | Green | Accounting | Approve invoices | Parking Lot | Emp 3 | 2025-03-16 | 2025-05-02 | 0
2 | New Structure | Project Tracker | Yellow | Customer Exp | Activity 5 | Parking Lot | Me (myslef) | 2025-04-03 | 2025-04-28 | 0
3 | Project B | Project Tracker | Green | N/A | Activity 11 | Parking Lot | Emp 6 | 2025-02-15 | 2025-05-02 | 0
4 | Project F | Automation Center | Yellow | Field Operations | Activity 15 | Parking Lot | Emp 2 | 2025-03-03 | 2025-04-29 | Need to cal XXX
Complete
No. | Project | Category | Health | Department | Activity | Status | Owner | Start Date | Due Date | Notes
1 | New Contract Temp | Project Tracker | Red | Sales | Revise current template | Complete | Emp 4 | 2025-04-08 | 2025-04-29 | 0
2 | New Hardware | Project Tracker | Yellow | IT | Activity 2 | Complete | Emp 5 | 2025-04-05 | 2025-04-29 | 0
3 | Ecom Site | Project Tracker | Green | Accounting | Activity 8 | Complete | Emp 5 | 2025-04-15 | 2025-05-13 | 0
4 | Customer Lifecycle | Project Tracker | Red | Customer Exp | Activity 9 | Complete | Emp 3 | 2025-02-28 | 2025-04-30 | Emp 3 on holiday
Cancelled
No. | Project | Category | Health | Department | Activity | Status | Owner | Start Date | Due Date | Notes
1 | Org Salary Tier | Project Tracker | Green | N/A | Activity 7 | Cancelled | Emp 4 | 2025-03-05 | 2025-05-28 | 0
2 | Project C | Project Tracker | Green | Development | Activity 12 | Cancelled | Emp 1 | 2025-03-19 | 2025-05-17 | 0
3 | Project D | Project Tracker | Green | Development | Activity 13 | Cancelled | Emp 3 | 2025-04-13 | 2025-05-19 | 0
Design: Ability to make thsi into an very attractive/interactive Dashboard for Presentations, etc. I've seen excel experts create remarkable looking worksheets that look like art.
All info fed from the "Action Sheet"
1. Each 'box' increases/decreases as information is pushed out/pulled in from Action Sheet.
2. Each box autosizes as necessary.
3. "Complete" and "Cancelled" boxes are ever-growing. Keeps history.

## Action Sheet
No. | Project | Category | Health | Risk | Impact | Effort | Department | Activity | Status | Owner | Start Date | Due Date | Notes
1 | FY26 Budget | Top 3 | Yellow | Low | High | High | N/A | Finalize Q2 budget before board meeting | Active | Me (myslef) | 2025-01-05 | 2025-04-29 | Waiting on COGS from accounting
2 | NDA | Workflow Bottlenecks | Red | Med | Med | Low | HR/Legal | Legal hasn’t reviewed a contract in 10 days | Active | Emp 1 | 2025-03-09 | 2025-04-29 | 4/12: I've asked Lou to contact legal
3 | New CRM | Project Tracker | Red | High | High | Low | Sales | CRM migration (Q2 goal) | Active | Emp 2 | 2025-04-01 | 2025-04-29 | 4/1: Testing in Sandbox
4 | Billing | Transactional Tasks | Green | Low | Low | High | Accounting | Approve invoices | Parking Lot | Emp 3 | 2025-03-16 | 2025-05-02
5 | Ops Meeting | Automation Center | Green | Low | Low | Low | N/A | Auto-generate weekly ops review | Active | Emp 4 | 2025-04-09 | 2025-05-18
6 | TS Training | Workflow Bottlenecks | Green | Low | High | High | Tech Support | Create training Outline | Active | Emp 5 | 2025-03-22 | 2025-06-07 | Missing XXX
7 | TS Tier Outline | Workflow Bottlenecks | Red | Med | Med | Low | Tech Support | Finalize employee skill assessment | Active | Emp 6 | 2025-01-28 | 2025-04-23
8 | New Contract Temp | Project Tracker | Red | High | High | Low | Sales | Revise current template | Complete | Emp 4 | 2025-04-08 | 2025-04-29
9 | KPI Development | Top 3 | Green | Low | Low | High | Field Operations | List the top 5 KPIs for Field Managers | Active | Emp 3 | 2025-02-06 | 2025-05-15
10 | OS upgrades | Transactional Tasks | Green | Low | Low | Low | IT | Activity 1 | Active | Emp 4 | 2025-03-17 | 2025-07-03 | Employee to call Vendo
11 | New Hardware | Project Tracker | Yellow | Low | High | High | IT | Activity 2 | Complete | Emp 5 | 2025-04-05 | 2025-04-29
12 | NDA Review | Automation Center | Green | Med | Med | Low | HR/Legal | Activity 3 | Active | Emp 1 | 2025-03-29 | 2025-06-05
13 | CRM Workflow | Project Tracker | Red | High | High | Low | Sales | Activity 4 | Active | Emp 3 | 2025-04-22 | 2025-03-13
14 | New Structure | Project Tracker | Yellow | Low | Low | High | Customer Exp | Activity 5 | Parking Lot | Me (myslef) | 2025-04-03 | 2025-04-28
15 | New Billing System | Top 3 | Yellow | Low | Low | Low | Accounting | Activity 6 | Active | Emp 5 | 2025-04-20 | 2025-04-29 | Invoices missing from system
16 | Org Salary Tier | Project Tracker | Green | Low | High | High | N/A | Activity 7 | Cancelled | Emp 4 | 2025-03-05 | 2025-05-28
17 | Ecom Site | Project Tracker | Green | Med | Med | Low | Accounting | Activity 8 | Complete | Emp 5 | 2025-04-15 | 2025-05-13
18 | Customer Lifecycle | Project Tracker | Red | High | High | Low | Customer Exp | Activity 9 | Complete | Emp 3 | 2025-02-28 | 2025-04-30 | Emp 3 on holiday
19 | Project A | Project Tracker | Yellow | Low | Low | High | N/A | Activity 10 | Active | Me (myslef) | 2025-04-17 | 2025-05-01
20 | Project B | Project Tracker | Green | Low | Low | Low | N/A | Activity 11 | Parking Lot | Emp 6 | 2025-02-15 | 2025-05-02
21 | Project C | Project Tracker | Green | Low | High | High | Development | Activity 12 | Cancelled | Emp 1 | 2025-03-19 | 2025-05-17
22 | Project D | Project Tracker | Green | Med | Med | Low | Development | Activity 13 | Cancelled | Emp 3 | 2025-04-13 | 2025-05-19
23 | Project E | Top 3 | Yellow | High | High | Low | Tech Support | Activity 14 | Active | Emp 2 | 2025-04-12 | 2025-05-18
24 | Project F | Automation Center | Yellow | Low | Low | High | Field Operations | Activity 15 | Parking Lot | Emp 2 | 2025-03-03 | 2025-04-29 | Need to cal XXX
25 | Project G | Workflow Bottlenecks | Yellow | Low | Low | Low | Tech Support | Activity 16 | Active | Emp 3 | 2025-04-08 | 2025-05-01
26 | Project H | Automation Center | Yellow | Low | High | High | N/A | Activity 17 | Active | Me (myslef) | 2025-04-10 | 2025-04-29 | Budget is tight
Design: Ability to make this into an attractive worksheet? Presentations
1. Ability to sort by any of the colums (may be a simple Filter function). Ability to focus on an employee, category, etc -without impacting the table nor Dashboard. While emailing/presenting sections to people.
2. "Category" selection feeds the Dashboard worksheet. Along with pertinent data.
3. Macro to add rows/activities.
4. Ability to remove unused rows (macro)
5. When an activity status changes to:
- Cancelled: removed from this table and added to Dashboard worksheet.
- Complete: removed from this table; added to Dashboard
- Parking Lot: removed from this table; added to Dashboard. BUT....
Need to be able to bring back to this table once it becomes active.
Note on D2: Mark Chiaravalloti: Drop Down
Note on E2: Mark Chiaravalloti: Overall Health evaluates "Due Date" and Risk" Risk Expire in Health Summary Low 8 or more Green Low risk, far from due date Low 3–7 Green Low risk, approaching due date Low 2 or fewer Yellow Low risk, urgent timeline Med 8 or more Green Medium risk, plenty of time Med 3–7 Yellow Medium risk, needs monitoring Med 2 or fewer Red Medium risk, urgent — escalate High 8 or more Yellow High risk, but time to act High 3–7 Red High risk, approaching deadline High 2 or fewer Red High risk, urgent deadline (Any) (Missing/Invalid) Gray Missing or invalid Risk or Due Date DUE DATE Metrics: Green: Due Date 8+ days from today. Yellow: Due Date is w/in 3-7 days from today. Red: Due date is 2 or fewer days from today.
Note on F2: Mark Chiaravalloti: Low: Goal clear. Owner capable. Dependencies in place Medium Some unknowns. Minor blockers. High Critical dependencies unclear, delays, &/or repeated issues
Note on G2: Mark Chiaravalloti: The levl of value, outcome, influence on the org/team. Low: Will not change results or momentum. Medium: Helpful or supportive of goals, but not transformative. High: Moves the needle. Drives strategy, growth, results (even culture).
Note on H2: Mark Chiaravalloti: Amount of time, energy, or complexity required to complete. Low: Effort Quick, simple, small amount of reources. Often repetitive. Medium: Requires some level of planning &/or collaboration. High: Complex, cross-functional, multi-step.
Note on I2: Mark Chiaravalloti: Drop-Down
Note on K2: Mark Chiaravalloti: Drop Down
Note on N2: Mark Chiaravalloti: DUE DATE Metrics: Green: Due Date 8+ days from today. Yellow: Due Date is w/in 3-7 days from today. Red: Due date is 2 or fewer days from today. Grey: Blank or non date in cell

## Data
CATEGORY |  | STATUS | DEPARTMENT | RISK, IMPACT & EFFORT
Top 3 |  | Active | Tech Support | Low
Workflow Bottlenecks |  | Cancelled | Field Operations | Med
Project Tracker |  | Complete | Customer Exp | High
Transactional Tasks |  | Parking Lot | Sales
Automation Center |  |  | Development
IT
Accounting
HR/Legal
N/A
Top 3 | Daily executive focus — the 3 most valuable actions What it is: My daily mission-critical focus — the 3 most important things I must push forward today. Why it matters: Without this, my day gets hijacked by noise. Force discipline and maitain strategic action. What goes here: - High-impact tasks - Things that only you can do - Often time-sensitive or decision-critical Examples: * Finalize Q2 budget before board meeting * Prepare talking points for CEO * Approve critical vendor contract * Address a top talent retention issue How to categorize: Ask: “If I only got 3 things done today, which ones would truly move the business forward?” Goal: No more than three
Workflow Bottlenecks | Real-time visibility into delays or blockers What it is: A place to track stalled processes, delays, and blockers that slow down teams or impacts delivery. Why it matters: Bottlenecks kill momentum. This section gives you early-warning radar so you can unblock teams proactively. What goes here: - Projects behind schedule - Delayed decisions or approvals - Cross-functional misalignment - Repeated inefficiencies Examples: * Legal hasn’t reviewed a contract in 10 days * A hiring manager keeps ghosting candidates * Procurement is holding up implementation * Onboarding process has delays every month How to categorize: Ask: “Is something stuck, waiting, or consistently behind?”
Project Tracker | Progress tracking on multi-week initiatives tied to org goals What it is: Your quarterly or long-term initiatives, tracked by stage and progress. Why it matters: This keeps us future-facing — even while buried in daily fires. It’s the bridge from now to next. What goes here: - Initiatives tied to OKRs or org-wide goals - Cross-functional or high-complexity work - Projects with measurable outcomes Examples: * CRM migration (Q2 goal) * Launching customer experience program * Revamping onboarding flow * Redesigning budgeting process How to categorize: Ask: “Is this something I need to drive or monitor over weeks/months that impacts the future of the org?”
Transactional Tasks | Management of daily ops, approvals, and admin work What it is: A running list of all low-complexity, repeatable, and short-cycle tasks — the daily grind. Why it matters: These are the things that eat your time. Putting them in one place helps you delegate, batch, or automate them. What goes here: - Approvals, email follow-ups - Document reviews - Internal requests - Calendar or travel tasks Examples: * Approve invoice * Respond to HR compliance check * Review timesheet exception * Update team meeting agenda How to categorize: Ask: “Does this take under 30 min, happen often, or not need me specifically?”
Automation Center | Inventory of workflows to streamline and automate What it is: A list of workflows I want to automate or systematize in the future. Why it matters: Every time I say “Why am I doing this manually again?” — Consider future automation. What goes here: - Repeatable steps - Time-consuming but structured processes - Tasks others do inconsistently - Ideas for system improvement Examples: * Auto-generate weekly ops review * Trigger alert when project is overdue * Send Slack when approval is submitted * Pre-fill onboarding task lists for new hires How to categorize: Ask: “Can this be done by a system or checklist? Could I teach someone or build a rule for it?”
This tab is used only to provide teh 'list dropdown' in other tabs.